## 01_Transformation_Plan
Workstream | Initiative | Objective / Outcome | Owner | 5Flow | Peer | Start Date | End Date | Status | RAG | Success Metrics | Dependencies | Risks | 2026-04-07 | 2026-04-08
Governance | Reporting | Board and Executive updates - every 2 weeks (Updates shared on email) | Peer |  | Jagan
Governance | Reporting | Block calendars for interim and final reviews | 5FLow |  | Jagan
Governance | Reporting | Prepare communication for ELT Meeting | 5Flow |  | Jagan
Contracts and Financial | SOW | Engaging Legal Core Team | 5FLow |  | Sriram
Contracts and Financial | SOW | Create legal / compliance checklist | 5FLow |  | Jagan
Contracts and Financial | SOW | Legal review of people plan | 5FLow | Vijai | Jagan
Contracts and Financial | SOW | Heads up to Legal on SOW review starting from March 16 | 5Flow | Vijai | Jagan
Contracts and Financial | SOW | Draft Contract, SoW | Peer | Vijai | Jagan
Contracts and Financial | SOW | Refine financial structure - Pricing and terms | Peer | Vijai | Jagan
Contracts and Financial | SOW | Review Contract / SOW | 5Flow |  | Jagan
Contracts and Financial | SOW | Finalize Pricing and Financials | Peer | Sriram | Rajesh
Contracts and Financial | SOW | Submit SOW for Legal review | Peer | Vijai | Jagan
Contracts and Financial | SOW | Legal review of SOW (Including Iterations) | 5Flow |  | Jagan
Contracts and Financial | SOW | Final SOW | Peer | Vijai | Jagan
5Flow AI Studio | Deployment | Pre-requisites - Readiness | Peer | Kishore | Sriram | 2026-03-23 | 2026-03-27 | Completed | Green
5Flow AI Studio | Deployment | Introduction Session to Pilot users | Peer |  | Subbiah | 2026-03-30 | 2026-03-30 | Completed | Green
5Flow AI Studio | Deployment | Studio Rollout for Pilot users (Code Insight and Spec agents) | Peer |  | Sriram | 2026-04-01 | 2026-04-06
5Flow AI Studio | Deployment | Support and Clarification session | Peer |  | Subbiah | 2026-04-06 | 2026-04-10
5Flow AI Studio | Deployment | Workshop on Pilot Usecases | Peer |  | Sriram | 2026-04-06 | 2026-04-10
5Flow AI Studio | Deployment | Pilot Period | Peer |  | Subbiah | 2026-04-01 | 2026-04-24
5Flow AI Studio | Deployment | Pilot feedback | Peer |  | Sriram | 2026-04-13 | 2026-04-17
5Flow AI Studio | Deployment | Introduction Session to Users | Peer |  | Subbiah | 2026-04-24 | 2026-04-24
5Flow AI Studio | Deployment | Phase 1 Rollout (Beyond pilot users) | Peer |  | Sriram | 2026-04-27 | 2026-04-27
5Flow AI Studio | Deployment | Release of Product, Ask AI and UI Copilot agents | Peer |  | Subbiah | 2026-05-11 | 2026-05-11
5Flow AI Studio | Deployment | Release of ADR, Coder | Peer |  | Subbiah | 2026-06-08 | 2026-06-08
5Flow AI Studio | Deployment | Release of Testing and OPS related agent | Peer |  | Subbiah | TBC
5Flow AI Studio | Deployment | Release of Agent Development environment and Orchestration | Peer |  | Subbiah | TBC
New Ways of Working | Enablement | Training and Certification on Spec Driven Development and New ways | Peer |  | Mathangi
TMO | Onboarding | Identify core team members, key Product Leadership and set up TMO | Peer | Vijai | Jagan
TMO | Onboarding | Onboard key people into the TMO - 5Flow (Product Leadership, Support Leaders etc) | 5Flow | Vijai | Jagan
TMO | Onboarding | Onboard key people into the TMO - Peer (Program Manager, Current Leads, Support Leaders) | Peer | Vijai | Jagan
TMO | Governance | Target Operating Model - Refined and Updated | Peer | Vijai | Jagan
TMO | Governance | Set-up governance model - communication, tracking, risk management | Peer | Vijai | Jagan
TMO | Governance | Transformation Pillar (Right Shoring) : Review, Socialize with Key Members - incorporate valid inputs | 5Flow | Vijai | Jagan
TMO | Governance | Transformation Pillar (Role Redundancy) : Review, Socialize - incorporate valid inputs | 5Flow | Vijai | Jagan
TMO | Execution | Build the first 30, 60, 90 day post signing execution plan | Peer | Vijai | Jagan
Wave | KT | Propelis business overview (Video) | Peer |  | Satish | 2026-04-06 | 2026-04-07
Wave | KT | PHP Boot Camp | Peer |  | Satish | 2026-04-06 | 2026-04-10
Wave | KT | Peer AI - New Ways of Working - Hands on Sessions | Peer |  | Mathangi
Wave | KT | HubX Functional and Technical Overview | 5FLow |  | Muthu / Anish | 2026-04-07 | 2026-04-08
Wave | KT | Code Insights for Wave 2 | Peer |  | Satish/Murugesan | 2026-04-07 | 2026-04-10
Wave | KT | Code Insights for Wave 3 | Peer |  | Satish/Murugesan | 2026-04-13 | 2026-04-17
Wave | KT | Peer AI Studio / 5Flow Studio Setup & Proficiency | Peer |  | Murugesan | 2026-04-08 | 2026-04-10
Wave | KT | Wave 2- Product Demo | 5FLow |  | Jagan | 2026-04-06 | 2026-04-10
Wave | KT | Wave 3 - Product Demo | 5FLow |  | Jagan | TBC | TBC
Wave | KT | Wave Client Configurations | 5FLow |  | Jagan | 2026-04-07 | 2026-04-10
Wave | KT | Wave - SDLC Process (Sprint Management, Review Steps) | 5FLow |  | Jagan | 2026-04-07 | 2026-04-10
Wave | KT | Wave - Solution Consultant - Process | 5FLow |  | Jagan | 2026-04-07 | 2026-04-10
Wave | KT | Wave - Support Model - KT | 5FLow |  | Jagan | 2026-04-07 | 2026-04-10
Wave | KT | R&R for the Team | Peer |  | Satish | TBC | TBC
MediaBox | KT |  | Peer |  | Murugesan
DragonFly | KT |  | Peer |  | Murugesan
Resource | Onboarding | Identifying resources, allocation on Runn | Peer |  | Satish/Retheesh | 2026-04-06 | 2026-04-10
Resource | Onboarding | Propelis Onboarding | Peer |  | Satish/Retheesh | 2026-04-06 | 2026-04-10
Resource | Onboarding | Code Base Access / Setup | Peer |  | Murugesan | 2026-04-06 | 2026-04-10
Resource | Onboarding | Cloud Access / Devops | Peer |  | Murugesan | 2026-04-06 | 2026-04-10

## 02_Dependency_Tracker
Dependency ID | Impacted Workstream | Description | Type | Owner | Dependent On | Target Date | Status | Risk | Mitigation | Escalation
D-01

## 03_Action_Tracker
Action ID | Action Description | Source | Owner | Priority | Due Date | Status | Closure Criteria | Notes
A-01

## 06_KT_Master
Workstream | Product / Platform | KT Scope | KT Owner | SME | Receiving Team | Start Date | End Date | Current Stage | Overall Status
Media Box

## 08_SteerCo_Dashboard
Metric | Value
Total Initiatives | 56
Green | 2
Amber | 0
Red | 0

## 09_Pivot_Summary
RAG by Workstream
Workstream | Green | Amber | Red | Total
Governance | 0 | 0 | 0 | 0
Tooling | 0 | 0 | 0 | 0
Ways of Working | 0 | 0 | 0 | 0
KT Progress
Total KT Waves | 1
KT Waves In Progress | 0
KT Waves Completed | 0